## bugs
CPSC 427 - Bug List for Seekers (Team 23)
Issue # | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce | Comments
8 | 2024-10-08 | Samuel | P0 | Resolved | Samuel | Environment setup | Development environment should be set up for both Windows and Mac | Environment setup may be incomplete or not working on all platforms | N/A - Feature | 1. Set up development environment on Windows 2. Set up development environment on Mac 3. Ensure code compiles on both platforms 4. Test basic functionality on both platforms
9 | 2024-10-08 | Amir | P3 | Resolved | Amir | Establish project structure in GitHub | Project directory structure should be set up in the repository | Project structure may be missing or incomplete | N/A - Feature | 1. Create necessary directories (src, include, assets, etc.) 2. Set up initial file structure 3. Add placeholder files if needed 4. Commit and push structure to GitHub
10 | 2024-10-08 | Jacob | P0 | Resolved | Jacob | Implement basic window creation and rendering loop | Game window should be created and basic rendering loop should work | Window creation or rendering loop may be missing or not functioning | N/A - Feature | 1. Set up window creation using graphics library 2. Implement basic game loop 3. Clear and update screen each frame 4. Test window creation and rendering
13 | 2024-10-08 | Brendon | P1 | Resolved | Brendon | Establish the ECS system for the game | Entity Component System should be set up for the game | ECS system may be missing or incomplete | N/A - Feature | 1. Create basic Entity class 2. Implement Component base class 3. Set up System interface 4. Create Registry for managing entities and components 5. Test basic ECS functionality
14 | 2024-10-09 | Samuel | P3 | Resolved | Samuel | Create a file for input manager | A file for managing inputs should be created | Input manager file may be missing | N/A - Feature | 1. Create a new file for input management 2. Add stub functions for different input types 3. Ensure file is properly included in project
18 | 2024-10-09 | Ahmed | P3 | Resolved | Ahmed | Create and upload ECS design for M1 | ECS design document for Milestone 1 should be created and uploaded | ECS design document may be missing or not uploaded | N/A - Feature | 1. Create ECS design document 2. Include all relevant components and systems 3. Ensure design matches implementation plans 4. Upload document to appropriate location
20 | 2024-10-09 | Amir | P2 | Resolved | Amir | Create Components and ComponentContainers based on the UML diagram | Components and ComponentContainers should be implemented as per UML | Components or ComponentContainers may be missing or not matching UML | N/A - Feature | 1. Review UML diagram 2. Create all necessary Component classes 3. Implement ComponentContainer for each Component type 4. Ensure implementations match UML specifications
22 | 2024-10-09 | Samuel | P3 | Resolved | Samuel | Attack cooldown component | An attack cooldown component should be added | Attack cooldown functionality may be missing | N/A - Feature | 1. Create AttackCooldown component 2. Add necessary properties (e.g., cooldown time, current cooldown) 3. Implement cooldown logic 4. Integrate component with attack system
24 | 2024-10-09 | Brendon | P3 | Resolved | Jacob | Singleton design for Registry | Registry should be implemented as a singleton | Registry may not be using singleton design pattern | N/A - Feature | 1. Modify Registry class to use singleton pattern 2. Ensure only one instance of Registry can be created 3. Provide global access point to the Registry instance 4. Test singleton behavior of Registry
29 | 2024-10-09 | Ahmed | P4 | Resolved | Ahmed | Create a file (or add to common) for all global variables | A file for global variables should be created for gameplay fine-tuning | Global variables may not be centralized or easily accessible | N/A - Feature | 1. Create a new file for global variables 2. Add at least one global variable as an example 3. Ensure the file is properly included where needed
39 | 2024-10-10 | Jacob | P3 | Resolved | Jacob | Add a timer class | A timer class should be implemented for time-based functionality | Timer functionality may be missing | N/A - Feature | 1. Create a Timer class 2. Implement start, stop, and reset methods 3. Add elapsed time calculation 4. Test timer functionality
16 | 2024-10-11 | Jacob | P1 | Resolved | Jacob | Handle inputs | Input handling for various game actions should be implemented | Input handling may be missing or incomplete | N/A - Feature | 1. Implement movement input (WASD) 2. Implement rotation input (Q/E) 3. Implement aiming with mouse position 4. Implement dodge/dash with spacebar 5. Implement attack inputs (left/right mouse buttons)
47 | 2024-10-11 | Samuel | P3 | Resolved | Samuel | Add team Comp and update player attack to use it | Team component should be added and player attack should consider team affiliation | Team-based attacks may not be implemented | N/A - Feature | 1. Create team component 2. Add team component to relevant entities 3. Update player attack logic to check team affiliation 4. Test team-based attack behavior
35 | 2024-10-12 | Ahmed | P1 | Resolved | Ahmed | Implement Basic Collision Detection Between Player and Environment | Player should not be able to move through walls and obstacles | Collision detection may be missing or not working correctly | N/A - Feature | 1. Define collision boxes for player and environment 2. Implement CollisionSystem for overlap detection 3. Prevent player movement through solid objects 4. Test collision prevention in various scenarios
42 | 2024-10-12 | Amir | P2 | Resolved | Amir | Implement update motion in Physics system | Physics system should update entity motion based on velocity and acceleration | Motion updates may be missing or incorrect | N/A - Feature | 1. Create Physics.hpp file 2. Implement step function for motion updates 3. Update velocity with acceleration 4. Update position with velocity 5. Update angle with rotation_velocity
50 | 2024-10-12 | Jacob | P2 | Resolved | Jacob | Implement Camera, View Matrix, and Projection Matrix | Camera system with view and projection matrices should be implemented | Camera system may be missing or incomplete | N/A - Feature | 1. Implement Camera class 2. Create view matrix calculation 3. Create projection matrix calculation 4. Integrate matrices into rendering pipeline
53 | 2024-10-12 | Jacob | P3 | Resolved | Jacob | Comp for all entities that rotate with player | A component for entities that rotate with the player should be implemented | Entities may not be rotating correctly with the player | N/A - Feature | 1. Create a new component for rotation with player 2. Implement rotation logic in the component 3. Apply the component to relevant entities 4. Test entity rotation behavior
56 | 2024-10-12 | Amir | P3 | Resolved | Amir | Improve handle input | Input handling should be improved for better responsiveness or functionality | Current input handling may be suboptimal | 1. Run the game 2. Press WASD 3. Response is slow between input and rendering
11 | 2024-10-13 | Samuel | P2 | Resolved | Samuel | Display a simple sprite as the player on the screen | A player sprite should be visible on the screen | Player sprite may not be displayed correctly | 1. Run the game 2. Player sprite is not displayed on the screen
34 | 2024-10-13 | Samuel | P1 | Resolved | Samuel | Implement Basic Player Movement and Camera Following | Player should move with WASD keys and camera should follow player | Player movement or camera following may be missing or incorrect | 1. Run the game 2. Press WASD keys 3. No change observed - player does not move with key press
38 | 2024-10-13 | Ahmed | P2 | Resolved | Ahmed | Implement Camera Rotation Controls | Camera should rotate using Q and E keys, affecting world orientation | Camera rotation controls may be missing or not working correctly | 1. Run the game 2. Press Q or E keys 3. No change observed - camera does not rotate with key press
60 | 2024-10-13 | Brendon | P3 | Resolved | Brendon | Add handle_input_per_frame and attack cooldown loop in world | Input handling per frame and attack cooldown system should be implemented | Input handling and attack cooldown may be missing or incomplete | N/A - Feature | 1. Implement handle_input_per_frame function 2. Add attack cooldown loop in world update 3. Test input handling responsiveness 4. Verify attack cooldown functionality
63 | 2024-10-13 | Amir | P3 | Resolved | Amir | Refactor EntityFactory | EntityFactory should be refactored for improved structure or functionality | EntityFactory may have suboptimal structure or functionality | N/A - Feature | 1. Review current EntityFactory implementation 2. Identify areas for improvement 3. Refactor EntityFactory code 4. Test entity creation after refactoring
65 | 2024-10-13 | Jacob | P3 | Resolved | Jacob | Move_with rotate_with comps and system | Movement and rotation components and systems should be implemented | Movement and rotation functionality may be missing or incomplete | N/A - Feature | 1. Create move_with component 2. Create rotate_with component 3. Implement corresponding systems 4. Test movement and rotation functionality
67 | 2024-10-13 | Ahmed | P3 | Resolved | Ahmed | Add Weapon and Wall Textures | Weapon and wall textures should be added to the game | Weapon and wall textures are missing | N/A - Feature | 1. Create or obtain weapon textures 2. Create or obtain wall textures 3. Add textures to the appropriate asset folder 4. Implement texture loading for weapons and walls
68 | 2024-10-13 | Samuel | P3 | Resolved | Samuel | Components for bouding box and texture | Bounding box and texture components should be implemented | Bounding box and texture components are missing or incomplete | N/A - Feature | 1. Create bounding box component 2. Create texture component 3. Implement necessary methods for each component 4. Test component functionality
71 | 2024-10-13 | Amir | P2 | Resolved | Amir | Update EntityFactory to incorporate texture and boundingbox comps | EntityFactory should create entities with texture and bounding box components | EntityFactory may not be incorporating texture and bounding box components | N/A - Feature | 1. Modify EntityFactory 2. Add texture component creation 3. Add bounding box component creation 4. Test entity creation with new components
74 | 2024-10-13 | Ahmed | P3 | Resolved | Ahmed | M1 Submission: Create Test Plan Document and Upload it to Docs | A test plan document should be created and uploaded to the /doc folder | Test plan document is missing or not in the correct location | N/A - Documentation | 1. Create a test plan document 2. Outline how to user-test the game 3. Include key presses and mouse actions 4. Upload the document to /doc folder
80 | 2024-10-13 | Amir | P4 | Resolved | Ahmed | Refactor data folder to src | Project structure should be organized with audio, meshes, and textures in src folder | Audio, meshes, and textures are not in the src folder | N/A - Code Organization | 1. Check current project structure 2. Move audio and meshes folders to src 3. Move files from /data/textures to /src/textures
85 | 2024-10-13 | Brendon | P2 | Resolved | Brendon | Fix and refactor collision system (use bounding box) | Collision system should use bounding boxes for accurate detection | Collision system may not be using bounding boxes, leading to inaccurate detection | 1. Run the game 2. Shoot projectile through enemy 3. Collision is not working | 1. Implement collision system 2. Test collisions between entities 3. Observe inaccurate collision detection
#88 | 2024-10-13 | Jacob | P0 | Resolved | Amir | Game crashes when player and projectile simultaneously collide with enemy | Game should handle multiple collisions gracefully, even if an entity is destroyed | Game crashes due to assertion failure in component container when accessing deleted enemy entity | 1. Create scenario where player and projectile move towards an enemy 2. Time it so both player and projectile collide with enemy on same frame 3. Observe game crash | -
#89 | 2024-10-13 | Jacob | P5 | Resolved | Jacob | Feat: Bullet doesn't preserve rotational velocity when fired while rotating both the play and the camera | Bullet should travel in an arcing path preserving both linear and rotational velocity when fired while rotating | Bullet only preserves linear velocity and travels in a straight line, ignoring rotational velocity | 1. Start the game and control the player 2. Begin rotating the player 3. While rotating, fire a bullet 4. Observe the bullet's path - it will travel in a straight line instead of an arc | -
#95 | 2024-10-13 | Samuel | P4 | Resolved | Amir | Bug: Projectiles don't despawn at defined weapon range | Projectiles should be deleted when they exceed the weapon range defined in the weapon stat struct | Projectiles continue flying indefinitely, ignoring the defined weapon range | 1. Start the game 2. Fire the weapon in any direction 3. Observe the projectile as it travels 4. Verify that the projectile continues beyond its defined range, potentially flying indefinitely | -
#96 | 2024-10-13 | Amir | P0 | Resolved | Amir | Bug: Game crashes on right-click | Right-clicking should either perform a specific in-game action or do nothing, without crashing the game | The game immediately crashes and closes when the player right-clicks | 1. Start the game 2. Navigate to any playable area or menu where mouse input is accepted 3. Perform a right-click action with the mouse 4. Observe that the game crashes and closes | -
#97 | 2024-10-13 | Amir | P3 | Resolved | Samuel | Bug: Incorrect rendering order - weapon appears below player | Weapon should be rendered on top of the player character, with at least the handle visible | Weapon is rendering below the player character, making it partially or completely invisible when equipped | 1. Start the game and control the player character 2. Equip or pick up a weapon (Note: for M1 weapon is equipped by default) 3. Observe the player character from an angle where the weapon should be visible. Move and rotate the camera. 4. Notice that the weapon is either partially obscured or completely hidden behind the player sprite | -
#98 | 2024-10-13 | Samuel | P4 | Resolved | Jacob | Bug: Weapon is rendered upside down | Weapon should be rendered in an upright position, with handle at the bottom and business end pointing upwards | Weapon appears upside down when equipped, with handle at the top and business end pointing downwards | 1. Start the game and control the player character 2. Equip or pick up a weapon 3. Observe the orientation of the weapon 4. Notice that the weapon is rendered upside down | Note: we know how to fix this, but we left is as feature for now as it looks cool
#99 | 2024-10-13 | Ahmed | P4 | Resolved | Jacob | Bug: Weapon and health bar incorrectly rotate around the player | Weapon and health bar should rotate with the player, maintaining their relative positions | Weapon and health bar orbit around the player when the player rotates | 1. Start the game and control the player character 2. Equip a weapon and ensure the health bar is visible 3. Rotate the player character 4. Observe that the weapon and health bar rotate around the player instead of with the player | -
#100 | 2024-10-13 | Jacob | P2 | Resolved | Ahmed | Bug: No defined boundary for game space - player can walk indefinitely | Player should be restricted from moving beyond the intended game area or map boundaries | Player can walk indefinitely in any direction, potentially leaving the intended game space | 1. Start the game and control the player character 2. Choose any direction and continue moving in that direction 3. Observe that the player can keep moving without encountering any boundaries 4. Repeat in different directions to confirm lack of boundaries | -
#101 | 2024-10-13 | Brendon | P2 | Resolved | Amir | Bug: Attack cooldown not functioning - player can spam projectiles | There should be a cooldown period between attacks, preventing rapid firing of projectiles | Player can continuously fire projectiles without any delay, bypassing the intended cooldown | 1. Start the game and control the player character 2. Initiate an attack to fire a projectile 3. Immediately attempt to fire another projectile 4. Observe that the second projectile can be fired without any cooldown delay 5. Repeat the process rapidly to confirm projectiles can be spammed | -
#111 | 2024-10-13 | Brendon | P4 | Resolved | Brendon | Feature: Implement Audio System and Sound Effects | Game has background music and appropriate sound effects for player actions (footsteps, dashing, attacking) | No audio implemented | N/A - Feature | 1. Set up audio system in the game engine 2. Add and implement background music 3. Create and implement footstep sound effects 4. Create and implement dash sound effect 5. Create and implement attack sound effect 6. Ensure all sounds match game style and player actions 7. Add audio controls to game settings
#116 | 2024-10-13 | Ahmed | P3 | Resolved | Amir | Bug: Player slides along entities after collision and stops only when outside the bounding box | Player should immediately stop moving when colliding with an entity and when movement keys are released, without sliding along the entity's edge or penetrating its bounding box | Player slides along the edge of the colliding entity and only stops when they've moved completely outside the entity's bounding box, even when no movement keys are being pressed | 1. Move the player towards a wall or other fixed entity 2. Collide with the wall at an angle 3. Release all movement keys (W, A, S, D) 4. Observe that the player continues to slide along the wall until they're outside its bounding box
#120 | 2024-10-14 | Amir | P4 | Resolved | Ahmed | Bug: Entity stacking and wall clipping issues | Entities (including player) should not be able to pass through walls under any circumstances | Stacked entities can push player through walls; player can clip through walls with persistent effort | 1. For entity stacking: Cluster multiple enemies near a wall, position player between them and the wall 2. For wall clipping: Repeatedly attempt to move through a wall from different angles 3. Observe that in both cases, passing through the wall is possible
#121 | 2024-10-14 | Amir | P4 | Resolved | Ahmed | Bug/Improvement: Circular bounding box causes inconsistent wall collision | Player should move smoothly along walls without visible penetration or bouncing | Player slightly enters and exits walls when moving along them due to circular bounding box | 1. Move player character to any straight wall 2. Attempt to move along the wall, parallel to its surface 3. Observe player's movement closely 4. Notice slight wall penetration and bouncing effect
#122 | 2024-10-14 | Jacob | P4 | Resolved | Jakob | Bug: Health bars not centered correctly under entities | Health bars should be perfectly centered beneath their respective entities, maintaining alignment with 3D depth effect | Health bars are misaligned and not centered correctly under entities due to separate rendering layer and lack of proper scene graph implementation | 1. Start the game and observe any entity with a visible health bar 2. Notice that the health bar is not centered correctly under the entity 3. Move the entity or camera to different positions to confirm persistent misalignment
#131 | 2024-10-15 | Jacob | P3 | Resolved | Amir | Bug: Enemies are not bounded by the map | Enemies should be bounded by the map like players | Enemies when in patrol mode can go outside the map boundaries if they are spawn near the map edges | 1. Start the game and explore the edges of the map 2. Observe if there are any enemies spawned near the edges 3. Notice enemies near edges can patrol outside the map boundaries
#142 | 2024-10-30 | Samuel | P2 | Resolved | Ahmed | Bug: Wall collision boundaries don't properly align with rotated walls, causing incorrect collision detection. The system only considers scale but not rotation when creating and checking wall collisions. | - Wall collision boundaries should perfectly match the visual representation of walls - Collision detection should work correctly regardless of wall rotation angle | - Collision boundaries are misaligned for rotated walls - Particularly noticeable with vertical walls (90-degree rotation) - Can cause players/entities to collide with invisible barriers or pass through visible walls | 1. Create a wall with rotation using EntityFactory::create_wall() with non-zero angle 2. Example: EntityFactory::create_wall({x, y}, PI / 2.0f, glm::vec2(length, 1.0f)) 3. Observe collision boundary misalignment when you play the game
#144 | 2024-10-30 | Amir | P0 | Resolved | Amir | Bug: Game crashes when player health depletes | Game should transition to death screen or game over state | Application crashes | Let player health reach zero
#145 | 2024-10-30 | Ahmed | P1 | Resolved | Jakob | Bug: Z key only hides window but doesn't terminate program | Program should fully terminate when Z is pressed | Window hides but audio continues and process remains active | Press Z key during gameplay
#146 | 2024-10-30 | Samuel | P0 | Resolved | Amir | Bug: Game crashes when projectiles hit dead enemies | Projectiles should pass through or be destroyed | Game crashes on collision | 1. Kill an enemy 2. Shoot projectiles at dead enemy corpse
#147 | 2024-10-30 | Ahmed | P2 | Resolved | Amir | Bug: Enemies can continuously attack without limitation | Enemies should have attack cooldown and limitations | Enemies spam attacks continuously | Engage with enemy in combat
#148 | 2024-10-30 | Samuel | P2 | Resolved | Jakob | Bug: Attack animation breaks during rapid attacks | Animation should play smoothly regardless of attack | Animation malfunctions when attacks are spammed | Rapidly press attack button
#149 | 2024-10-30 | Amir | P3 | Resolved | Amir | Feat: Add death timer for entities | Entities should have a timed death state before disappearing | Not implemented
#150 | 2024-10-30 | Amir | P3 | Resolved | Amir/Jakob | Feat: Add energy system for actions | - Dodging should consume energy - Attacking should consume energy - Energy should regenerate over time | Not implemented
#151 | 2024-10-30 | Ahmed | P3 | Resolved | Amir | Feat: Improve dodge mechanics | Entities should be invulnerable while dodging | Not implemented
#152 | 2024-10-30 | Jakob | Future Release | Open | Ahmed | Feat: Add textures to weapons and projectiles | All weapons and projectiles should have proper textures | Not implemented
#153 | 2024-10-30 | Ahmed | P3 | Resolved | Jakob | Feat: Add FPS counter to game screen | Game window should display current FPS in window caption or game screen. If game screen, it should have a button to toggle it on and off. | Not implemented
#154 | 2024-10-30 | Brendon | P3 | Resolved | Brendon | Feat: Add tutorial to game | Game should have a tutorial to guide players through the controls and mechanics | Not implemented
#155 | 2024-10-30 | Samuel | P4 | Resolved | Jakob | Feat: Add restart functionality | Game should restart after player death | Not implemented
#156 | 2024-10-30 | Jakob | P5 | Resolved | TBD | Feat: Add loading screen | Game should have a loading screen before starting and on restart | Not implemented
#157 | 2024-11-02 | Amir | P3 | Resolved | TBD | Doc: Create comprehensive test plan for M2 requirements | Complete test plan document covering all M2 features | Test plan needs updating for M2 |  | 1. Document test cases for Game AI 2. Document test cases for Animation 3. Document test cases for Assets 4. Document test cases for Mesh Collision 5. Document test cases for Help System 6. Document test cases for FPS Counter 7. Document test cases for Playability
#158 | 2024-11-02 | Ahmed | P3 | Resolved | TBD | Doc: Update bug-report.xlsx with all M2 issues | Complete bug tracking spreadsheet | Spreadsheet needs updating |  | 1. Add all resolved M1 issues 2. Add all new M2 issues 3. Update status and assignments 4. Add severity classifications
#159 | 2024-11-02 | Samuel | P3 | Resolved | TBD | Doc: Create 4-minute demonstration video | Video showing all M2 features and implementation | Video needs to be created |  | 1. Record title screen 2. Demo all M2 requirements 3. Show code implementation 4. Add clear text overlays
#160 | 2024-11-02 | Jakob | P3 | Resolved | TBD | Doc: Update README with M2 implementation details | README contains all M2 feature documentation | README needs M2 section |  | 1. Document implementation details 2. Add code references 3. Update build instructions
#161 | 2024-11-02 | Brendon | P3 | Resolved | TBD | Doc: Create and populate M2_Submission branch | Branch contains all required M2 deliverables | Branch needs to be created |  | 1. Create branch from main 2. Add all documentation 3. Verify completeness
#162 | 2024-11-02 | Ahmed | P3 | Resolved | Ahmed/Jakob | Feat: Implement dynamic mesh vertex extraction for projectiles | - Function to extract actual vertices from mesh - Remove hardcoded vertices in create_projectile - Proper convex hull collision detection using real mesh data | Currently using hardcoded edge vertices |  | Steps to complete: 1. Create vertex extraction function 2. Update create_projectile function 3. Test with various projectile meshes
#163 | 2024-11-02 | Amir | P4 | Resolved | TBD | Improvement: Entity collision push back feels unnatural | Natural-feeling collision response between entities | Push back values create unrealistic movement |  | Steps to complete: 1. Test different push back values 2. Try removing push back 3. Implement most natural-feeling solution
#164 | 2024-11-02 | Ahmed | P4 | Open | TBD | Bug: Various wall visibility glitches | Walls should properly occlude vision in all cases | - Can see through walls when standing adjacent - Screen turns black when backing against wall | 1. Stand next to wall and rotate camera 2. Put character's back against wall and face forward
#166 | 2024-11-02 | Samuel | P4 | In-Progress | Ahmed | Bug: Enemies can pass through walls during push back interactions | Enemies should remain bounded by walls regardless of push back | Enemies clip through walls when: - Enemy walks backward while being pushed - Multiple enemies push player against wall | 1. Push enemy while they're walking backward near wall 2. Get multiple enemies to push player against wall | Related Issues: #163 (Entity Collision Push Back)
#167 | 2024-11-02 | Amir | P3 | Resolved | Amir | Feat: Multiple AI improvements needed for better gameplay | - AI should have proper vision detection - Improved pathfinding - Better weapon angle calculations - Enhanced battle logic | - AI can detect through walls - Basic pathfinding only - Static weapon angles - Simple battle logic |  | 1. Implement vision/line of sight 2. Enhance pathfinding algorithm 3. Add dynamic weapon angle calculations 4. Improve battle decision making
#168 | 2024-11-02 | Amir | Future Release | Open | Amir | Feat: Add footstep sounds for enemy entities | Enemies should have audible footsteps like the player | Only player has footstep sounds | 1. Extend audio system to enemies 2. Add footstep sound triggers 3. Test with multiple enemies
#169 | 2024-11-02 | Amir | Future Release | Open | TBD | Feat: Implement weapon drops from defeated enemies | Enemies should drop their weapons upon defeat | No weapon drops implemented |  | Planned for Milestone 3
| 2024-11-19 | Ahmed | P5 | Open | TBD | Feat: Save at bonfire | Save should happen automatically at bonfire | Save through keyboard keys
#164 | 2024-11-16 | Jakob | P4 | Open | TBD | Bug: Various wall visibility glitches | Walls should properly occlude vision in all cases | - Can see through walls when standing adjacent - Screen turns black when backing against wall | 1. Stand next to wall and rotate camera 2. Put character's back against wall and face forward
#166 | 2024-11-16 | Samuel | P4 | In-Progress | Ahmed | Bug: Enemies can pass through walls during push back interactions | Enemies should remain bounded by walls regardless of push back | Enemies clip through walls when: - Enemy walks backward while being pushed - Multiple enemies push player against wall | 1. Push enemy while they're walking backward near wall 2. Get multiple enemies to push player against wall | Related Issues: #163 (Entity Collision Push Back)
| 2024-11-16 | Amir | P4 | Open | TBD | Bug: Zombie AI attack you before you are within attack range | Zombie AI attack should attack only within attack range | Zombie AI attack you before you are within attack range | 1. Walk close to zombie AI but from distance 2. Zombie will attack outside range

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release